## Project Plan Template
Project Name | Arijit Bose |  |  | Overall Progress 4 |  |  |  |  | Duration 4 | #REF! | TOTAL TASKS 4 | #REF!
Project Name | Excel Project Planner | [7 empty] | Project Start 4 | #REF! | Completed | #REF!
Project Background | This is a excel project planner which can be used to plan any project efficiently. It has task grid, Gnatt chart, and formula based cells for faster calculation. | [7 empty] | Project End 4 | #REF! | In progress | #REF!
[9 empty] | Man-days 4 | #REF! | Not Started | #REF!
Project Schedule | [8 empty] | Gantt Chart
Tasks | Responsible | Start Date | End Date | Progress | Status | Duration | Completed | Pending
Task Title 1 | Person 1 | 2022-03-19 | 2022-04-20 | 100% | Completed | 32 | 32 | 0
Task Title 2 | Person 2 | 2022-03-20 | 2022-04-30 | 50% | In progress | 41 | 20.5 | 20.5
Task Title 3 | Person 3 | 2022-03-23 | 2022-03-27 | 100% | Completed | 4 | 4 | 0
Task Title 4 | Person 4 | 2022-03-22 | 2022-03-28 | 45% | In progress | 6 | 2.7 | 3.3
Task Title 5 | Person 5 | 2022-04-02 | 2022-04-15 | 60% | In progress | 13 | 7.8 | 5.2
Task Title 6 | Person 6 | 2022-03-28 | 2022-04-17 | 0% | Not Started | 20 | 0 | 20
Task Title 7 | Person 7 | 2022-04-07 | 2022-04-16 | 40% | In progress | 9 | 3.6 | 5.4
Task Title 8 | Person 8 | 2022-04-17 | 2022-04-30 | 0% | Not Started | 13 | 0 | 13
Task Title 9 | Person 9 | 2022-05-03 | 2022-06-13 | 0% | Not Started | 41 | 0 | 41
Task Title 10 | Person 10 | 2022-05-06 | 2022-05-31 | 100% | Completed | 25 | 25 | 0
Task Title 11 | Person 1 | 2022-05-05 | 2022-05-14 | 75% | In progress | 9 | 6.75 | 2.25
Task Title 12 | Person 2 | 2022-05-09 | 2022-05-30 | 50% | In progress | 21 | 10.5 | 10.5
Task Title 13 | Person 3 | 2022-05-05 | 2022-06-17 | 50% | In progress | 43 | 21.5 | 21.5
Task Title 14 | Person 4 | 2022-05-11 | 2022-06-25 | 0% | Not Started | 45 | 0 | 45
Task Title 15 | Person 5 | 2022-05-05 | 2022-05-20 | 0% | Not Started | 15 | 0 | 15
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
i
Help?